## Sheet1
MOM¦ Project kick off ¦ 19-10-210
1 | Requirement Analysis 1. initial Brain stroming meeting planned (22-10-2018 ¦ 13:30) 2. Requirement Freeze for initial customer review (24-10-2018 ¦ 11:30)
2 | Identified the individual roles and back up person for each role PM – Christopher(Aju) Test Manager – Aju(Christopher) HW Manager – Hannes(Juli) Integrator – Japun(Hannes)
3 | All documents will placed in Github. If professor is not comfortable, management document will placed in Elli
4 | Project – Holiday (Tuesday) – project members can work on tuesday
5 | weekly customer meeting proposal Monday or Wednesday 4th block